Department of Commerce

U.S. Census Bureau

2010 Census Early Operations

American Recovery and Reinvestment Act Program Plan

Department of Commerce

U.S. Census Bureau

2010 Census Early Operations ARRA Program Plan

Table of Contents

Funding Table

Objectives

Activities

Characteristics

Delivery Schedule

Environmental Review Compliance

Savings or costs

Measures

Monitoring/Evaluation

Transparency

Accountability

Barriers to Effective Implementation

Federal Infrastructure Investments

Funding Table

The American Recovery and Reinvestment Act (ARRA) provided $1 billion to help the Census Bureau conduct a successful Census in 2010. This plan focuses on $750 million being provided for early 2010 Census Field Operations, which all occur in FY 2010.

Objectives

The funding provided in the ARRA will support the following Department of Commerce goals:

- DOC Strategic Goal 1: “Maximize U.S. competitiveness and enable economic growth for American industries, workers, and consumers.”

- DOC Strategic Objective 1.3: “Advance key economic and demographic data that support effective decision-making of policymakers, businesses, and the American public.”

- Performance Outcome:  “Provide benchmark measures of the U.S. population, economy, and governments (ESA/CENSUS)”

- ESA/Census Outcome Measure: “Complete key activities for cyclical census programs on time to support effective decision-making by policymakers, businesses, and the public meet constitutional and legislative mandates.”

The ARRA funding will be used to conduct the following early 2010 operations:

- Group Quarters (GQ) Operations include the enumeration of college dormitories, prisons, nursing homes, etc.  These operations include:

- Group Quarters Validation (GQV) Operation provides updated addresses and spatial information for use in the Group Quarters Advance Visit, Group Quarters Enumeration, Service-Based Enumeration, Military Group Quarters Enumeration, Enumeration at Transient Locations, and subsequent enumeration universes.  The primary purposes of this operation are (1) to verify if a specific address is a Group Quarters, a housing unit, or non-residential, and (2) if it is a group quarters, determine the type of group quarters to help us plan the actual enumeration.

- Group Quarters Advance Visit (GQAV) Operation informs the Group Quarters (GQs) contact person of the upcoming GQ enumeration, addresses privacy and confidentiality concerns, and identifies any security issues.

- Group Quarters Enumeration (GQE) Operation visits group quarters (including military GQs), develops a control list of all residents, assigns an address status code, and distributes questionnaires for completion.

- Update/Enumerate (U/E) Operation is a method of data collection conducted in communities with special enumeration needs and where many housing units may not have house-number-and-street-name mailing addresses.

- Update/Leave (U/L) Field operation canvasses geographic areas where the type of the address does not indicate the location of the housing unit or the delivery point for receiving mail does not ensure that the mail gets to the correct unit (e.g., mailbox banks are broken and mail is left at a central location).

- Local Census Office (LCO) Staffing Operation provides the personnel in all 494 LCOs necessary to support field operations.  This staff does the behind-the-scenes work, like payroll, required for the 2010 Census to function.

Activities

- Group Quarters (GQ) Operations:

  - The Group Quarters Validation (GQV) Operation supports the Census Bureau’s efforts to compile the most accurate Census Bureau address file using improved methodologies for data collection and coverage.  GQV verifies the address has the correct census geography, validates the address as a Group Quarter (GQ), housing unit, transient location, non-residential address, vacant unit, or address requiring deletion.  If validated as a GQ, GQV determines the type of GQ and collects all pertinent information about the GQ.

  - The Group Quarters Advance Visit (GQAV) Operation is dependent upon the GQV Operation. Crew Leaders visit all GQs and meet with the designated contact person to verify the GQ name, address, contact name and phone number, and obtain an expected Census Day population count so that the correct amount of enumeration materials can be prepared, and arrange a date for the enumeration at the facility. The operation also researches potential GQ adds.

  - The Group Quarters Enumeration (GQE) Operation, census enumerators visit group quarters (including military GQs), develop a control list of all residents, assign an address status code, and distribute questionnaires for completion. Within a few days, the enumerator returns to the GQ to collect completed questionnaires, obtain information for any missing items, and obtain census information for any missing questionnaires based on the control list prepared at the initial visit.

Some types of facilities, such as jails and prisons, are “self-enumerated” facilities. These facilities use census procedures to conduct the enumeration, and the facility employees become special sworn census employees to protect the confidentiality of the census information.

- The Update/Enumerate (U/E) Operation enumerators canvass assignment areas to update residential addresses, including adding living quarters that were not included on the address listing pages, update Census Bureau maps, and complete a questionnaire for each housing unit. For Census 2000, these areas included selected American Indian reservations, colonias (usually rural Spanish-speaking communities), and resort areas with high concentrations of seasonally vacant living quarters. Interviews are conducted using a paper questionnaire. Each housing unit is classified as Occupied, Vacant, or Delete. Completed questionnaires are shipped to the data capture centers. Registers and maps are shipped to National Processing Center (NPC) for data capture and digitizing.

- Update/Leave (U/L) Field Operation enumerators canvass the blocks in their assignment areas, update the address list and census maps, determine if the housing unit is a duplicate or does not exist and needs to be deleted, and delivers addressed census questionnaires to each unit. They also prepare and drop off questionnaires to any added housing units that they find in their assignment areas not on existing census address lists. These questionnaires are mailed back by the respondent.

- The Local Census Office (LCO) Staffing Operation recruits, hires, selects, and releases office and field staff; performs supervisory and non-supervisory functions for office activities and field operations; distributes training and procedural manuals for office staff; and trains employees and office staff for the field operations performed at the LCO.

Characteristics

The $750 million will be used to support early 2010 operations and will exclusively fund Federal in-house activities (primarily wages for temporary workers).  We believe that allocating the ARRA funding in this manner, especially to early operations, reduces operational and programmatic risks at this critical stage in the life cycle.

Delivery Schedule

August 10, 2009 – October 23, 2009			Group Quarters Validation

December 12, 2009 – March 19, 2001		Group Quarters Advance Visit

March 25, 2010 – May 21, 2010 			Group Quarters Enumeration

January 11, 2010 – April 2, 2010 			Update/Leave

February 22, 2010 – June 4, 2010			Update/Enumerate

October 1, 2009 – September 30, 2010		LCO Staffing Operation

Environmental Review Compliance

N/A

Savings or costs

N/A

Measures

All performance measures will be reported to the Department of Commerce on a quarterly basis and annual results will be published in the Annual Performance and Accountability Report

Measure:  At least 90% of key activities will be completed on schedule.

2010 Targets Using Base Funding:

- Complete Group Quarters validation and Group Quarters Advanced Visit operations.

- Conduct the 2010 Census (Mail out/Mail back, Update/Enumerate, Update/Leave, UU/L, Group Quarter Enumeration, ME, Remote Alaska, SBE, and ETL).

- Conduct Census Operations in Puerto Rico and the Island Areas.

- Conduct Nonresponse Followup operations.

- Begin Coverage Measurement field operations.

- Conduct Coverage Followup field operations.

Note: There is no incremental change in activity related to the ARRA funding.

Monitoring/Evaluation

The Census Bureau Chief Financial Officer’s organization establishes and operates a comprehensive financial management and internal controls program for the agency.  The robust accounting structure contains detailed coding that allows obligations and expenditures for all activities and operations to be individually tracked and monitored.

The Census Investment Review Board (CIRB) serves as the senior governance body for major investments. The board consists of senior program executives and is chaired by the Deputy Director. The Senior Advisor for Project Management facilitates the review of new initiatives and ongoing programs to identify and manage risks, and to monitor progress in achieving the desired program goals and objectives.  The Census Bureau’s major investments must also be presented to the Department of Commerce Investment Review Board, which conducts periodic reviews of the major programs and projects across all agencies and bureaus within the Department.

The Decennial program offices manage the 2010 Census program requirements, schedule and budget. Program management is centralized within the Decennial Management Division (DMD).  The 2010 Census program is divided into projects, and a program manager is assigned to each of these projects. The program managers oversee the budgets their assigned projects and work closely with the Census offices that participate in the projects to ensure that funds are being used to meet the project’s requirements, and to address any cost or schedule issues.

Monthly briefings are held with senior officials of the Department of Commerce and Office of Management and Budget (OMB) on the status of the 2010 Decennial Census program.  The Monthly Status Report (MSR), which is used as the basis of these briefings, includes information on status and progress of major decennial activities, including all major contracts being managed (including earned value metrics, schedule accomplishments, risks, and issues) as well as obligation and expenditure information.

Decennial management has established comprehensive project and contract management structures for the major Decennial contracts supporting the collection, tabulation, and dissemination of the 2010 Census data.  During the actual conduct of the Decennial Census (fiscal years 2009, 2010 and 2011), the 2010 Census Program also uses a Cost and Progress System to monitor costs and work completed daily for all major field operations. This ensures that there are no surprises and gives us an early warning to take corrective action, if necessary.

Transparency

The Census Bureau has established a new Treasury account to track the $1 billion received from the ARRA.  We have also established a financial structure, including unique coding that will allow us to separately track obligations and expenditures for each activity funded through ARRA and to aid in the transparency of these expenditures.  All financial transactions associated with this funding will be captured and retained in the Census Bureau’s Core Financial System.

The Census Bureau’s ARRA spend plan is being made available to the public on the recovery.gov website.  In addition, weekly reports will be completed and posted on the recovery.gov website.

Accountability

The Census Bureau has reporting requirements established by the Department of Commerce in response to guidelines established by OMB to monitor ARRA funding.  The Census Bureau’s Comptroller, according to those established guidelines, will monitor all ARRA funds.

The Acquisitions Program Management staff will also closely monitor work and progress on a daily basis.  In addition, a task manager is assigned to each task under the contract. Budget and program staff conduct detailed monthly reviews of obligations compared to the operating plans, and Census Bureau Executive Staff members, including the Director and Deputy Director are briefed regularly. Budget spending reports are also sent monthly to the Department of Commerce.

Monthly briefings are held with senior officials of the Department of Commerce and Office of Management and Budget (OMB) on the status of the 2010 Decennial Census program.

Barriers to Effective Implementation

Besides such longstanding challenges like the nation’s increasing cultural diversity, the Bureau also faces newly emerging issues such as local anti-illegal immigration campaigns and a post-September 11 environment that could potentially heighten some groups’ fears of government agencies.

Federal Infrastructure Investments

N/A

# Footnotes

ARRA Funding will begin October 1, 2009.