Department of Commerce

U.S. Census Bureau

2010 Census Partnership

American Recovery and Reinvestment Act Program Plan

Department of Commerce

U.S. Census Bureau

2010 Census Partnership

American Recovery and Reinvestment Act Program Plan

Table of Contents

Funding Table

Objectives

Activities

Characteristics

Delivery Schedule

Environmental Review Compliance

Savings or costs

Measures

Monitoring/Evaluation

Transparency

Accountability

Barriers to Effective Implementation

Federal Infrastructure Investments

Funding

The American Recovery and Reinvestment Act (ARRA) provided $1 billion to help the Census Bureau conduct a successful Census in 2010.  This plan focuses on $120 million that will be used to enhance the 2010 Census Partnership program.

Objectives

An additional 2,027 partnership staff (above the 680 already hired) will permit a greater outreach to population groups that are at higher risk of not being counted in 2010.  More staff will result in additional contacts with community organization leaders, greater presence at community events, and better follow-through with partner organizations that have agreed to partner with the Census Bureau.  Additional partnership staff can improve the census by informing the local census offices about potential barriers and related strategies that will help improve coverage in hard-to-count population areas.

Activities

Partnership staff will provide information and training about the 2010 Census to community-based organizations, religious leaders, educators, local businesses, and media outlets in designated hard-to-count areas.  An expanded Partnership presence will result in greater support from community leaders for the 2010 Census.  Residents in hard-to-count communities and neighborhoods will have a greater likelihood of knowing about the census and why they need to complete and return their questionnaire, which should help raise their response rate.

Characteristics

Funds allocated for the 2010 Census Partner Support Program enable the Census Bureau to hire 2,027 additional field partnership staff (1,750 Partnership Assistants and 277 other partnership staff) to support census outreach and promotion efforts with partners such as Complete Count Committees, religious organizations, schools, local and tribal governments and various community-based organizations.  Funding will also support the purchase of promotional items that will be used by partnership staff to promote the 2010 Census.

Delivery Schedule

December 2008	Launched Integrated Partner Contact Database (IPCD)

March 2009		Held National Partners Kick-off Meeting

May 1, 2009	 	Partnership Specialists start work

June 1, 2009		Partnership Assistants start work

May 30, 2010		Partnership Assistants conclude work

September 30, 2010	Partnership Specialists conclude work

Environmental Review Compliance

N/A

Savings or costs

N/A

Measures

All performance measures will be reported to the Department of Commerce on a quarterly basis and annual results will be published in the Annual Performance and Accountability Report

Measure: Partnership staff effectively engage community leaders and organizations, particularly in hard-to-count areas, with a civic engagement campaign that positively affects mail response rates, undercount, and public cooperation.

2009 Targets Using Base Funding:

- 680 Partnership Staff hired and trained and begin developing partnerships with local organizations.

- Begin to identify locations for 30,000 Questionnaire Assistance Center and 40,000 Be Counted sites in hard-to-count areas.

- Continue the formation and training of Complete Count Committees.

2009 Targets Using Recovery and Reinvestment Act Funding:

- 2,707 total Partnership Staff  (100% hired) provide greater communication and follow-through with partner organizations, continue identifying locations for 30,000 Questionnaire Assistance Centers and 40,000 Be Counted sites in hard-to-count areas (40% complete), and continue the formation and training of approximately 10,000 Complete Count Committees (50% complete).  Partnership staff establish partnerships and work with approximately 70,000 organizations (60% of expected 120,000 organizational partnerships for 2010 Census).

2010 Targets Using Base Funding:

- 680 Partnership staff spearhead public events with thousands of community partners during Action Phase (January through April 2010) to raise participation levels in 2010 Census.

- Continue the formation and training of Complete Count Committees.

- 680 Partnership staff work with community partners to promote cooperation with enumerators ("Open Your Door" public campaign) during Nonresponse Followup phase (Late May through July) of 2010 Census.

2010 Targets Using Recovery and Reinvestment Act Funding:

- Under Development

Monitoring/Evaluation

The Census Bureau Chief Financial Officer’s organization establishes and operates a comprehensive financial management and internal controls program for the agency.  The robust accounting structure contains detailed coding that allows obligations and expenditures for all activities and operations to be individually tracked and monitored.

The Decennial program offices manage the 2010 Census program requirements, risks, schedule and budget. Program management is centralized within the Decennial Management Division (DMD).  The 2010 Census program is divided into projects, and a program manager is assigned to each of these projects. The program managers oversee the budgets of their assigned projects and work closely with the Census offices that participate in the projects to ensure that funds are being used to meet the project’s requirements, to mitigate risks and to address any cost or schedule issues.

Monthly briefings are held with senior officials of the Department of Commerce and Office of Management and Budget (OMB) on the status of the 2010 Decennial Census program.  The Monthly Status Report (MSR), which is used as the basis of these briefings, includes information on status and progress of major decennial activities, including all major contracts being managed (including earned value metrics, schedule accomplishments, risks, and issues) as well as obligation and expenditure information.

Decennial management has established comprehensive project and contract management structures for the major Decennial contracts supporting the collection, tabulation, and dissemination of the 2010 Census data.  During the actual conduct of the Decennial Census (fiscal years 2009, 2010 and 2011), the 2010 Census Program also uses a Cost and Progress System to monitor costs and work completed daily for all major field operations. This ensures that there are no surprises and gives us an early warning to take corrective action, if necessary.

Transparency

The Census Bureau has established a new Treasury account to track the $1 billion received from the ARRA.  We have also established a financial structure, including unique coding that will allow us to separately track obligations and expenditures for each activity funded through ARRA and to aid in the transparency of these expenditures.  All financial transactions associated with this funding will be captured and retained in the Census Bureau’s Core Financial System.

The Census Bureau’s ARRA spend plan is being made available to the public on the recovery.gov website.  In addition, weekly reports will be completed and posted on the recovery.gov website.

Accountability

The Census Bureau has reporting requirements established by the Department of Commerce in response to guidelines established by OMB to monitor ARRA funding.  The Census Bureau’s Comptroller, according to those established guidelines, will monitor all ARRA funds.

Budget and program staff conduct detailed monthly reviews of obligations compared to the operating plans. Census Bureau Executive Staff members, including the Director and Deputy Director are briefed regularly. Budget spending reports are also sent monthly to the Department of Commerce.

Monthly briefings are held with senior officials of the Department of Commerce and Office of Management and Budget (OMB) on the status of the 2010 Decennial Census program.

Barriers to Effective Implementation

The Census Bureau may experience challenges with recruiting partnership staff and securing agreements with partnership organizations with the right skill sets, contacts, and abilities to reach hard-to-count groups.

Federal Infrastructure Investments

N/A